## 📖 How to Use
CMMI v3.0 — GRC Assessment Tool
Performance Improvement Assessment — Guidance & Instructions
⚠ Important: What CMMI Is (and Is Not)
CMMI is a Performance Improvement Model | CMMI (Capability Maturity Model Integration) is a process improvement framework — not a technical compliance standard or a cybersecurity control framework. ISACA, which now stewards CMMI, describes it as a model for improving organisational performance and capability maturity across people, processes, and technology. It is fundamentally different from frameworks such as ISO 27001, NIST CSF, SOC 2, or PCI-DSS, which prescribe specific controls and are used for external audit and certification. CMMI instead describes how well an organisation's processes are defined, managed, measured, and optimised — and uses appraisals (not audits) to assess that maturity. Key implication for GRC teams: Do NOT treat this checklist as a list of controls to tick off. Instead, use it to evaluate process capability and identify improvement opportunities.
How to Use the Master Checklist
Step 1 Scope & Filter | Before reviewing any practice, use the filter columns to scope the checklist to your organisation: • PA Category — filter by domain (Engineering, Managing, Improving, etc.) • Applicability — filter out Practice Areas not relevant to your organisation type (e.g., safety-critical PAs for a pure IT shop) • Practice Level — filter to your target maturity level (e.g., show only Level 1–2 for an initial appraisal) • Practice Priority — start with High-priority practices for a focused assessment • Org Size — tailor scope to Small/Medium/Large org context
Step 2 Assign Owners | For each in-scope practice, assign a responsible owner in the 'Owner' column. This person is accountable for gathering evidence and completing the status assessment — not necessarily the subject matter expert.
Step 3 Rate Status | Use the dropdown in the 'Implementation Status' column to select one of: • Not Started — no activity yet • In Planning — approach defined but not yet executed • Partially Implemented — practice is in progress, evidence exists but incomplete • Fully Implemented — practice is consistently performed with strong evidence • Not Applicable — practice has been scoped out (document rationale in Notes)
Step 4 Document Evidence | Use the 'Notes / Evidence' column to record evidence references (document names, links, or system references). For a formal CMMI appraisal, evidence must be objective and verifiable.
Step 5 Score in PA Summary | Once owners complete their assessments, use the 'PA Summary & Scores' sheet to record aggregate scores (0–5) per Practice Area and track progress toward your target maturity level.
Priority & Applicability Guidance
Practice-Level Priority | Practice Priority reflects how foundational a practice is to CMMI maturity: • High — Foundational practices (Level 1–2). Required for even minimal capability demonstration. • Medium — Defined practices (Level 3). Important for organisations targeting structured, repeatable processes. • Low — Advanced practices (Level 4–5). Relevant only for organisations pursuing quantitative management and optimisation.
PA-Level Priority | Practice Area Priority is a GRC team judgement call on how central that PA is to your organisation's context. It is pre-populated as a starting point and should be reviewed and adjusted based on your organisation's sector, size, and strategic objectives.
Not All PAs Apply to All Orgs | Example deprioritisations: • Enabling Safety (ESAF) — skip for pure IT/software shops; only relevant for safety-critical domains • Enabling Virtual Work (EVW) — skip for co-located teams • Service Delivery PAs (SDM, STSM) — skip for product engineering orgs with no service delivery function • Engineering PAs (PI, TS, VV) — skip for IT service management orgs with no product development • Advanced PAs (MPM, PAD, PCM) — deprioritise for organisations targeting ML1–2
Sheets in This Workbook
• 📖 How to Use — This guidance page • ✅ Master Checklist — Full practice-level assessment with filtering and status tracking • 📊 PA Summary & Scores — Aggregate scores per Practice Area with target maturity and priority • 🗂 PA Category Guide — Reference: how CMMI Practice Areas map to domains and CMMI's intended use

## ✅ Master Checklist
CMMI v3.0 — Performance Improvement Assessment ¦ Master Checklist
CMMI is a process maturity & performance improvement model — not a control framework. Scope using Priority, Applicability, and PA Category filters before assessment. ¦ Source: ISACA CMMI v3.0
# | PA # | Practice Area | Abbrev | PA Category | Practice Level | Practice ID & Title | Practice Description | Key Activities / Sub-practices | Key Work Products | PA Priority | Practice Priority | Applicability | Org Size | Implementation Status | Owner | Notes / Evidence
1 | 1 | Service Delivery Management | SDM | Doing – Service | L1 – Initial / Foundation | SDM 1.1 — Use the service system to deliver services | Operate and use the service system to deliver services to customers. | Use a service system. | Service system | High | High | IT Services / Managed Services | All | Not Started
2 | 1 | Service Delivery Management | SDM | Doing – Service | L2 – Managed / Core | SDM 2.1 — Develop, record, keep updated, and follow service agreements | Establish and maintain formal service agreements with customers. | Develop, record, and keep the structure and format of the service agreement updated. | Service agreement | High | High | IT Services / Managed Services | All | Not Started
3 | 1 | Service Delivery Management | SDM | Doing – Service | L2 – Managed / Core | SDM 2.2 — Receive and process service requests in accordance with service agreements | Manage the end-to-end lifecycle of service requests. | Receive service requests and ensure each request is within scope. | Service requests | High | High | IT Services / Managed Services | All | Not Started
4 | 1 | Service Delivery Management | SDM | Doing – Service | L2 – Managed / Core | SDM 2.3 — Deliver services in accordance with service agreements | Operate the service system to fulfil service requests. | Operate service system components according to procedures. | List of services provided | High | High | IT Services / Managed Services | All | Not Started
5 | 1 | Service Delivery Management | SDM | Doing – Service | L2 – Managed / Core | SDM 2.4 — Analyze existing service agreements and service data | Prepare for updated or new service agreements through analysis. | Collect customer and end user needs and service provider concerns. | Service data analysis results | High | High | IT Services / Managed Services | All | Not Started
6 | 1 | Service Delivery Management | SDM | Doing – Service | L2 – Managed / Core | SDM 2.5 — Develop, record, and follow the service system operations approach | Define the approach for operating and changing the service system. | Define the approach for service system operation and each change. | Service system operation and change approach | High | High | IT Services / Managed Services | All | Not Started
7 | 1 | Service Delivery Management | SDM | Doing – Service | L2 – Managed / Core | SDM 2.6 — Confirm the readiness of the service system | Verify the service system is ready to support service delivery. | Confirm that service system components and tools are operational. | Readiness reports | High | High | IT Services / Managed Services | All | Not Started
8 | 1 | Service Delivery Management | SDM | Doing – Service | L3 – Defined | SDM 3.1 — Develop, record, and use organizational standard service systems and agreements | Standardize and maintain service systems and agreements across the organization. | Review and prioritize standardization and maintenance needs. | Approach or process for standardized service agreements and service systems | High | Medium | IT Services / Managed Services | All | Not Started
9 | 2 | Strategic Service Management | STSM | Doing – Service | L1 – Initial / Foundation | STSM 1.1 — Develop a list of current services | Identify and record all current services offered. | Identify current services. | List of current services | Medium | High | IT Services / Managed Services | Medium–Large | Not Started
10 | 2 | Strategic Service Management | STSM | Doing – Service | L2 – Managed / Core | STSM 2.1 — Develop, keep updated, and use descriptions of current services | Maintain accurate individual service descriptions and a service catalog. | Develop, record, and keep individual service descriptions updated. | Individual service descriptions | Medium | High | IT Services / Managed Services | Medium–Large | Not Started
11 | 2 | Strategic Service Management | STSM | Doing – Service | L2 – Managed / Core | STSM 2.2 — Collect, record, and analyze data about strategic needs and capabilities | Inform strategic planning with analysis of capabilities and needs. | Collect and analyze data on capabilities. | Analysis results | Medium | High | IT Services / Managed Services | Medium–Large | Not Started
12 | 2 | Strategic Service Management | STSM | Doing – Service | L2 – Managed / Core | STSM 2.3 — Develop, keep updated, and follow an approach for providing new or changed services | Align new or changed services with strategic needs and capabilities. | Develop, record, and confirm strategic business objectives. | Descriptions of strategic objectives | Medium | High | IT Services / Managed Services | Medium–Large | Not Started
13 | 2 | Strategic Service Management | STSM | Doing – Service | L3 – Defined | STSM 3.1 — Develop, keep updated, and use organizational standard service descriptions and service levels | Maintain standard service descriptions and levels across the organization. | Develop, record, and keep updated standard service descriptions. | Descriptions of service characteristics | Medium | Medium | IT Services / Managed Services | Medium–Large | Not Started
14 | 3 | Product Integration | PI | Doing – Engineering | L1 – Initial / Foundation | PI 1.1 — Assemble solutions and deliver to the customer | Integrate components and deliver the assembled solution with documentation. | Assemble solution. | Assembled solutions and documentation | High | High | Software / Hardware / Systems Dev | All | Not Started
15 | 3 | Product Integration | PI | Doing – Engineering | L2 – Managed / Core | PI 2.1 — Develop, keep updated, and follow an integration strategy | Define the strategy for integrating product components. | Identify and record product components to be integrated. | Product integration strategy | High | High | Software / Hardware / Systems Dev | All | Not Started
16 | 3 | Product Integration | PI | Doing – Engineering | L2 – Managed / Core | PI 2.2 — Develop, keep updated, and use the integration environment | Establish and maintain the environment used for product integration. | Develop requirements for the integration environment. | Verified and validated integration environment | High | High | Software / Hardware / Systems Dev | All | Not Started
17 | 3 | Product Integration | PI | Doing – Engineering | L2 – Managed / Core | PI 2.3 — Develop, keep updated, and follow procedures and criteria for integrating solutions | Define and use procedures and criteria for product integration. | Develop, use, and keep updated product integration procedures. | Product integration procedures | High | High | Software / Hardware / Systems Dev | All | Not Started
18 | 3 | Product Integration | PI | Doing – Engineering | L2 – Managed / Core | PI 2.4 — Confirm component readiness prior to integration | Verify each component is properly identified and meets requirements before integration. | Track the integration readiness status of components. | Acceptance documents or criteria for each product component | High | High | Software / Hardware / Systems Dev | All | Not Started
19 | 3 | Product Integration | PI | Doing – Engineering | L2 – Managed / Core | PI 2.5 — Evaluate integrated components for conformance | Assess integrated components against solution requirements and design. | Evaluate integrated components, interfaces, and testing using strategy, procedures, and criteria. | Integration evaluation results | High | High | Software / Hardware / Systems Dev | All | Not Started
20 | 3 | Product Integration | PI | Doing – Engineering | L2 – Managed / Core | PI 2.6 — Integrate solutions and components according to the integration strategy | Perform integration following the defined strategy. | Confirm readiness of the product integration environment. | Integrated solution or components | High | High | Software / Hardware / Systems Dev | All | Not Started
21 | 3 | Product Integration | PI | Doing – Engineering | L3 – Defined | PI 3.1 — Review and keep updated interface or connection descriptions throughout the solution life | Maintain interface/connection descriptions for coverage, completeness, and consistency. | Review and keep updated interface or connection descriptions with affected stakeholders. | Interface or connection review results | High | Medium | Software / Hardware / Systems Dev | All | Not Started
22 | 3 | Product Integration | PI | Doing – Engineering | L3 – Defined | PI 3.2 — Confirm component interfaces comply with descriptions prior to integration | Verify interfaces or connections match their descriptions before integration. | Compare interface descriptions with component interfaces and identify non-compliances. | Results of comparison of component interfaces to their descriptions | High | Medium | Software / Hardware / Systems Dev | All | Not Started
23 | 3 | Product Integration | PI | Doing – Engineering | L3 – Defined | PI 3.3 — Evaluate integrated components for interface or connection compatibility | Check that integrated components are compatible at interfaces/connections. | Evaluate the integrated components for compatibility. | Interface or connection issues reports | High | Medium | Software / Hardware / Systems Dev | All | Not Started
24 | 4 | Technical Solution | TS | Doing – Engineering | L1 – Initial / Foundation | TS 1.1 — Build a solution to meet requirements | Construct a solution that satisfies stated requirements. | Build a solution. | Product or service | High | High | Software / Hardware / Systems Dev | All | Not Started
25 | 4 | Technical Solution | TS | Doing – Engineering | L2 – Managed / Core | TS 2.1 — Design and build a solution to meet requirements | Create a detailed design and build the solution from it. | Define the architecture. | Architecture | High | High | Software / Hardware / Systems Dev | All | Not Started
26 | 4 | Technical Solution | TS | Doing – Engineering | L2 – Managed / Core | TS 2.2 — Evaluate the design and address identified issues | Review and improve the design through structured evaluations. | Determine what types of reviews to perform. | Design evaluation issues | High | High | Software / Hardware / Systems Dev | All | Not Started
27 | 4 | Technical Solution | TS | Doing – Engineering | L2 – Managed / Core | TS 2.3 — Provide guidance on use of the solution | Create and provide user guidance materials for the solution. | Develop and provide guidance materials. | Guidance material | High | High | Software / Hardware / Systems Dev | All | Not Started
28 | 4 | Technical Solution | TS | Doing – Engineering | L3 – Defined | TS 3.1 — Develop criteria for design decisions | Establish criteria to guide design choices throughout the lifecycle. | Analyze, develop, evaluate, use, and keep updated design criteria. | Design criteria | High | Medium | Software / Hardware / Systems Dev | All | Not Started
29 | 4 | Technical Solution | TS | Doing – Engineering | L3 – Defined | TS 3.2 — Develop alternative solutions for selected components | Generate and record alternatives for key components. | Develop, identify, and record alternative solutions. | Alternative solutions | High | Medium | Software / Hardware / Systems Dev | All | Not Started
30 | 4 | Technical Solution | TS | Doing – Engineering | L3 – Defined | TS 3.3 — Perform a build, buy, or reuse analysis | Determine the most appropriate sourcing strategy for solution components. | Perform a build, buy, or reuse analysis. | Build, buy, or reuse analysis | High | Medium | Software / Hardware / Systems Dev | All | Not Started
31 | 4 | Technical Solution | TS | Doing – Engineering | L3 – Defined | TS 3.4 — Select solutions based on design criteria | Choose the solution alternative that best satisfies the established criteria. | Evaluate each alternative solution against selection criteria. | Recorded solutions, evaluations, and rationale | High | Medium | Software / Hardware / Systems Dev | All | Not Started
32 | 4 | Technical Solution | TS | Doing – Engineering | L3 – Defined | TS 3.5 — Develop, keep updated, and use information needed to implement the design | Maintain the technical data package and traceability information. | Record the information needed to implement the solution. | Technical data package | High | Medium | Software / Hardware / Systems Dev | All | Not Started
33 | 4 | Technical Solution | TS | Doing – Engineering | L3 – Defined | TS 3.6 — Design solution interfaces or connections using established criteria | Define and document interface/connection design based on criteria. | Define interface or connection criteria. | Interface or connection selection criteria | High | Medium | Software / Hardware / Systems Dev | All | Not Started
34 | 5 | Peer Reviews | PR | Doing – Quality | L1 – Initial / Foundation | PR 1.1 — Perform reviews of work products and record issues | Identify issues in work products through informal or formal reviews. | Review work products to identify issues. | List of issues from work product reviews | Medium | High | All Organisations | All | Not Started
35 | 5 | Peer Reviews | PR | Doing – Quality | L2 – Managed / Core | PR 2.1 — Develop and keep updated peer review procedures and supporting materials | Establish documented procedures for conducting peer reviews. | Record and keep updated peer review procedures. | Procedures for preparing and performing peer reviews | Medium | High | All Organisations | All | Not Started
36 | 5 | Peer Reviews | PR | Doing – Quality | L2 – Managed / Core | PR 2.2 — Select work products to be peer reviewed | Identify which work products will undergo peer review. | Evaluate the criticality of the work product. | Work product or process selection criteria | Medium | High | All Organisations | All | Not Started
37 | 5 | Peer Reviews | PR | Doing – Quality | L2 – Managed / Core | PR 2.3 — Prepare and perform peer reviews on selected work products | Execute peer reviews following established procedures. | Develop schedule. | List of work products | Medium | High | All Organisations | All | Not Started
38 | 5 | Peer Reviews | PR | Doing – Quality | L2 – Managed / Core | PR 2.4 — Resolve issues identified in peer reviews | Take action on issues found during peer reviews. | Resolve issues. | Resolution of issues | Medium | High | All Organisations | All | Not Started
39 | 5 | Peer Reviews | PR | Doing – Quality | L3 – Defined | PR 3.1 — Analyze results and data from peer reviews | Use peer review data to identify process improvement opportunities. | Analyze peer review process data and the results from the peer review. | Analysis results | Medium | Medium | All Organisations | All | Not Started
40 | 6 | Process Quality Assurance | PQA | Supporting | L1 – Initial / Foundation | PQA 1.1 — Identify and address process and work product issues | Find, record, and resolve quality issues in processes and work products. | Identify issues. | Recorded issues | High | High | All Organisations | All | Not Started
41 | 6 | Process Quality Assurance | PQA | Supporting | L2 – Managed / Core | PQA 2.1 — Develop, keep updated, and follow a quality assurance approach and plan | Plan quality assurance activities based on historical data. | Develop, record, and keep updated the quality approach and plan. | Quality assurance approach and plan | High | High | All Organisations | All | Not Started
42 | 6 | Process Quality Assurance | PQA | Supporting | L2 – Managed / Core | PQA 2.2 — Objectively evaluate selected performed processes and work products | Use criteria and checklists to evaluate processes against standards. | Develop and keep updated clearly stated criteria for evaluations. | Criteria | High | High | All Organisations | All | Not Started
43 | 6 | Process Quality Assurance | PQA | Supporting | L2 – Managed / Core | PQA 2.3 — Communicate quality and non-compliance issues and ensure their resolution | Escalate and resolve noncompliance issues and identify quality trends. | Communicate and resolve each noncompliance issue. | Quality trend analysis results | High | High | All Organisations | All | Not Started
44 | 6 | Process Quality Assurance | PQA | Supporting | L2 – Managed / Core | PQA 2.4 — Record and use results of quality assurance activities | Maintain records of quality assurance results. | Record and keep updated information about quality assurance activities. | Evaluation records | High | High | All Organisations | All | Not Started
45 | 6 | Process Quality Assurance | PQA | Supporting | L3 – Defined | PQA 3.1 — Identify and record opportunities for improvement during quality assurance activities | Capture improvement ideas observed while performing quality assurance. | Record potential improvements observed during quality assurance activities. | Improvement proposals | High | Medium | All Organisations | All | Not Started
46 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L1 – Initial / Foundation | RDM 1.1 — Record requirements | Capture and record requirements for the work. | Record the requirements. | Recorded requirements | High | High | Software / IT Services / Systems Dev | All | Not Started
47 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L2 – Managed / Core | RDM 2.1 — Elicit stakeholder needs and confirm understanding of requirements | Gather and agree on stakeholder needs, expectations, constraints, and interfaces. | Develop criteria for identifying appropriate requirements providers. | Lists of agreed-upon requirements providers | High | High | Software / IT Services / Systems Dev | All | Not Started
48 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L2 – Managed / Core | RDM 2.2 — Transform stakeholder needs into prioritized customer requirements | Convert stakeholder inputs into prioritized, documented customer requirements. | Translate stakeholder needs into recorded customer requirements. | Prioritized customer requirements | High | High | Software / IT Services / Systems Dev | All | Not Started
49 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L2 – Managed / Core | RDM 2.3 — Obtain commitment from project participants to implement requirements | Ensure project participants can implement the requirements. | Assess the impact of requirements on existing commitments. | Impact assessment | High | High | Software / IT Services / Systems Dev | All | Not Started
50 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L2 – Managed / Core | RDM 2.4 — Develop, record, and keep updated bidirectional traceability among requirements | Maintain traceability between requirements and work products/activities. | Develop, record, and keep updated bidirectional requirements traceability. | Records of bidirectional requirements traceability | High | High | Software / IT Services / Systems Dev | All | Not Started
51 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L2 – Managed / Core | RDM 2.5 — Ensure plans and work products remain consistent with requirements | Identify and resolve inconsistencies between requirements and plans/work products. | Review plans, activities, and work products for consistency with requirements. | Records of inconsistencies between requirements, plans, and work products | High | High | Software / IT Services / Systems Dev | All | Not Started
52 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L3 – Defined | RDM 3.1 — Develop and keep requirements updated for the solution and its components | Maintain technical requirements for solution design and derived requirements. | Develop, record, and keep updated requirements in technical terms for design. | Requirements | High | Medium | Software / IT Services / Systems Dev | All | Not Started
53 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L3 – Defined | RDM 3.2 — Develop operational concepts and scenarios | Define operational concepts and scenarios to refine and discover requirements. | Develop, record, and keep updated operational concepts and scenarios. | Operational concepts and scenarios | High | Medium | Software / IT Services / Systems Dev | All | Not Started
54 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L3 – Defined | RDM 3.3 — Allocate the requirements to be implemented | Assign requirements to solution components. | Allocate, record, and keep updated requirements. | Requirement allocations | High | Medium | Software / IT Services / Systems Dev | All | Not Started
55 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L3 – Defined | RDM 3.4 — Identify, develop, and keep updated interface or connection requirements | Define and maintain requirements for interfaces and connections. | Identify, record, and keep updated internal and external interface requirements. | Interface or connection requirements | High | Medium | Software / IT Services / Systems Dev | All | Not Started
56 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L3 – Defined | RDM 3.5 — Ensure that requirements are necessary and sufficient | Analyse requirements for necessity and sufficiency. | Perform a requirements analysis to determine if requirements are necessary and sufficient. | Requirements analysis results | High | Medium | Software / IT Services / Systems Dev | All | Not Started
57 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L3 – Defined | RDM 3.6 — Balance stakeholder needs and constraints | Validate and balance requirements against stakeholder needs and constraints. | Develop and keep updated a definition of required functionality and quality attributes. | Operational concepts, scenarios, use cases, activity diagrams, and user stories | High | Medium | Software / IT Services / Systems Dev | All | Not Started
58 | 7 | Requirements Development & Management | RDM | Doing – Engineering | L3 – Defined | RDM 3.7 — Validate requirements to ensure the solution will perform as intended | Confirm requirements will result in a solution that performs as intended. | Identify and select validation techniques. | Selected validation techniques | High | Medium | Software / IT Services / Systems Dev | All | Not Started
59 | 8 | Verification & Validation | VV | Doing – Engineering | L1 – Initial / Foundation | VV 1.1 — Perform verification and record results | Verify that work products and solutions meet their requirements. | Perform verification of selected work products and solutions against their requirements. | Verification results | High | High | Software / Hardware / Systems Dev | All | Not Started
60 | 8 | Verification & Validation | VV | Doing – Engineering | L1 – Initial / Foundation | VV 1.2 — Perform validation and record results | Validate that solutions function as intended in their target environment. | Validate selected work products and solutions with stakeholders throughout the lifecycle. | Validation results | High | High | Software / Hardware / Systems Dev | All | Not Started
61 | 8 | Verification & Validation | VV | Doing – Engineering | L2 – Managed / Core | VV 2.1 — Select components and methods for verification and validation | Identify what will be verified/validated and how. | Select solution components for verification and validation. | Lists of solution components selected for verification and validation | High | High | Software / Hardware / Systems Dev | All | Not Started
62 | 8 | Verification & Validation | VV | Doing – Engineering | L2 – Managed / Core | VV 2.2 — Develop, keep updated, and use the verification and validation environment | Establish the environment needed to support verification and validation. | Identify requirements for the verification and validation environment. | Verification environment | High | High | Software / Hardware / Systems Dev | All | Not Started
63 | 8 | Verification & Validation | VV | Doing – Engineering | L2 – Managed / Core | VV 2.3 — Develop, keep updated, and follow procedures for verification and validation | Define and use documented procedures for VV activities. | Identify criteria for selecting work products and activities. | Verification procedures | High | High | Software / Hardware / Systems Dev | All | Not Started
64 | 8 | Verification & Validation | VV | Doing – Engineering | L3 – Defined | VV 3.1 — Develop, keep updated, and use criteria for verification and validation | Define criteria to guide and assess VV activities. | Develop verification and validation criteria and refine them as work progresses. | Verification criteria | High | Medium | Software / Hardware / Systems Dev | All | Not Started
65 | 8 | Verification & Validation | VV | Doing – Engineering | L3 – Defined | VV 3.2 — Analyze and communicate verification and validation results | Evaluate VV results and drive corrective actions. | Compare actual results to expected results. | Results of actual to expected comparisons for verification and validation | High | Medium | Software / Hardware / Systems Dev | All | Not Started
66 | 9 | Supplier Agreement Management | SAM | Managing | L1 – Initial / Foundation | SAM 1.1 — Identify, evaluate, and select suppliers | Choose qualified suppliers through a formal evaluation process. | Identify potential suppliers and distribute requests for proposals. | List of potential suppliers | Medium | High | All Organisations | All | Not Started
67 | 9 | Supplier Agreement Management | SAM | Managing | L1 – Initial / Foundation | SAM 1.2 — Develop and record the supplier agreement | Establish a formal written agreement with the selected supplier. | Develop and record a supplier agreement. | Supplier Agreement | Medium | High | All Organisations | All | Not Started
68 | 9 | Supplier Agreement Management | SAM | Managing | L1 – Initial / Foundation | SAM 1.3 — Accept or reject the supplier deliverables | Confirm that supplier deliverables meet contractual requirements. | Accept or reject the supplier deliverable based on the extent it meets contractual requirements. | Deliverables per the supplier agreement | Medium | High | All Organisations | All | Not Started
69 | 9 | Supplier Agreement Management | SAM | Managing | L1 – Initial / Foundation | SAM 1.4 — Process supplier invoices | Handle supplier invoices in accordance with agreements. | Process supplier invoices in accordance with agreements. | Records of supplier invoices | Medium | High | All Organisations | All | Not Started
70 | 9 | Supplier Agreement Management | SAM | Managing | L2 – Managed / Core | SAM 2.1 — Identify evaluation criteria, potential suppliers, and distribute supplier requests | Prepare and distribute a comprehensive supplier request package. | Develop the Statement of Work (SOW) for the supplier. | Records of reviews of the request package and stakeholder commitments | Medium | High | All Organisations | All | Not Started
71 | 9 | Supplier Agreement Management | SAM | Managing | L2 – Managed / Core | SAM 2.2 — Evaluate supplier responses and select suppliers | Use evaluation criteria to objectively score and select a supplier. | Verify conformance to requirements and completeness of supplier responses. | Supplier proposal | Medium | High | All Organisations | All | Not Started
72 | 9 | Supplier Agreement Management | SAM | Managing | L2 – Managed / Core | SAM 2.3 — Manage supplier activities and keep agreement updated | Monitor and manage supplier performance throughout the agreement term. | Establish supplier agreement. | Supplier agreement | Medium | High | All Organisations | All | Not Started
73 | 9 | Supplier Agreement Management | SAM | Managing | L2 – Managed / Core | SAM 2.4 — Verify supplier agreement is satisfied before accepting deliverables | Formally accept supplier deliverables after confirming agreement requirements are met. | Refine, update, or add, and use acceptance criteria and procedures. | Acceptance criteria and procedures | Medium | High | All Organisations | All | Not Started
74 | 10 | Continuity | CONT | Doing – Service | L1 – Initial / Foundation | CONT 1.1 — Develop contingency approaches for managing significant disruptions | Define high-level approaches and triggers for continuity situations. | Record contingency approaches. | Records of contingency approaches | Medium | High | IT Services / Critical Systems | All | Not Started
75 | 10 | Continuity | CONT | Doing – Service | L2 – Managed / Core | CONT 2.1 — Identify and prioritize functions essential for continuity | Determine which functions must continue or resume first during a disruption. | Develop continuity scenarios. | Prioritized list of critical functions | Medium | High | IT Services / Critical Systems | All | Not Started
76 | 10 | Continuity | CONT | Doing – Service | L2 – Managed / Core | CONT 2.2 — Identify and prioritize resources essential for continuity | Identify and rank resources needed to maintain or restore essential functions. | Identify and record internal and external dependencies. | Records of critical resources required for continuity | Medium | High | IT Services / Critical Systems | All | Not Started
77 | 10 | Continuity | CONT | Doing – Service | L2 – Managed / Core | CONT 2.3 — Develop, keep updated, and follow continuity plans | Create and maintain plans to resume performing essential functions. | Identify and record threats and vulnerabilities to ongoing operations. | List of threats and vulnerabilities | Medium | High | IT Services / Critical Systems | All | Not Started
78 | 10 | Continuity | CONT | Doing – Service | L3 – Defined | CONT 3.1 — Develop and keep updated materials for continuity training | Create training materials for continuity threats and scenarios. | Develop a strategy for conducting continuity training. | Continuity training strategy | Medium | Medium | IT Services / Critical Systems | All | Not Started
79 | 10 | Continuity | CONT | Doing – Service | L3 – Defined | CONT 3.2 — Provide and evaluate continuity training according to the plan | Deliver and assess continuity training effectiveness. | Deliver training that covers initiation and implementation of continuity plans. | Training records | Medium | Medium | IT Services / Critical Systems | All | Not Started
80 | 10 | Continuity | CONT | Doing – Service | L3 – Defined | CONT 3.3 — Prepare, conduct, and analyze results from verification and validation of the continuity plan | Formally test and validate the continuity plan through exercises. | Develop a plan for verifying and validating continuity. | Verification and validation plan for continuity | Medium | Medium | IT Services / Critical Systems | All | Not Started
81 | 11 | Incident Resolution & Prevention | IRP | Doing – Service | L1 – Initial / Foundation | IRP 1.1 — Record and resolve incidents | Capture, address, and track all incidents. | Record incidents. | Updated list of incidents and status | Medium | High | IT Services / Operations | All | Not Started
82 | 11 | Incident Resolution & Prevention | IRP | Doing – Service | L2 – Managed / Core | IRP 2.1 — Develop, keep updated, and follow an incident resolution and prevention approach | Establish a systematic approach for identifying and managing incidents. | Identify incidents. | Recorded incidents and information | Medium | High | IT Services / Operations | All | Not Started
83 | 11 | Incident Resolution & Prevention | IRP | Doing – Service | L2 – Managed / Core | IRP 2.2 — Monitor and resolve each incident to closure | Track incidents until resolved and close them formally. | Monitor incidents until they meet the terms of the customer agreement. | Updated list of incidents and status | Medium | High | IT Services / Operations | All | Not Started
84 | 11 | Incident Resolution & Prevention | IRP | Doing – Service | L2 – Managed / Core | IRP 2.3 — Communicate incident status | Keep customers and end users informed of incident status. | Communicate incident status. | Records of communications to customers and end users | Medium | High | IT Services / Operations | All | Not Started
85 | 11 | Incident Resolution & Prevention | IRP | Doing – Service | L3 – Defined | IRP 3.1 — Develop, keep updated, and use an incident management system | Maintain a controlled system for processing and tracking incidents. | Establish an incident management system. | An incident management system with controlled work products | Medium | Medium | IT Services / Operations | All | Not Started
86 | 11 | Incident Resolution & Prevention | IRP | Doing – Service | L3 – Defined | IRP 3.2 — Analyze selected incident and resolution data for prevention | Use incident data to prevent future occurrences. | Categorize the incident. | Updated incident management records | Medium | Medium | IT Services / Operations | All | Not Started
87 | 12 | Risk & Opportunity Management | RSK | Managing | L1 – Initial / Foundation | RSK 1.1 — Identify and record risks or opportunities and keep them updated | Capture all identified risks and opportunities. | Identify the risks associated with the work. | List of identified risks or opportunities | High | High | All Organisations | All | Not Started
88 | 12 | Risk & Opportunity Management | RSK | Managing | L2 – Managed / Core | RSK 2.1 — Analyze identified risks or opportunities | Assess impact and likelihood of risks and opportunities. | Analyze the identified risks. | Identified risks or opportunities | High | High | All Organisations | All | Not Started
89 | 12 | Risk & Opportunity Management | RSK | Managing | L2 – Managed / Core | RSK 2.2 — Monitor identified risks or opportunities and communicate status | Track and report risks and opportunities throughout the project. | Periodically review risks or opportunities. | Records of risk or opportunity monitoring | High | High | All Organisations | All | Not Started
90 | 12 | Risk & Opportunity Management | RSK | Managing | L3 – Defined | RSK 3.1 — Identify and use risk or opportunity categories | Organize risks and opportunities using a defined category scheme. | Identify risk or opportunity categories. | Categories list | High | Medium | All Organisations | All | Not Started
91 | 12 | Risk & Opportunity Management | RSK | Managing | L3 – Defined | RSK 3.2 — Define and use parameters for risk or opportunity analysis and handling | Apply quantitative parameters and thresholds to risk/opportunity analysis. | Identify a relative priority for each risk or opportunity based on assigned parameters. | Risk or opportunity evaluation, categorization, and prioritization parameters | High | Medium | All Organisations | All | Not Started
92 | 12 | Risk & Opportunity Management | RSK | Managing | L3 – Defined | RSK 3.3 — Develop and keep updated a risk or opportunity management strategy | Maintain an overall strategy for managing risks and opportunities. | Develop, record, and keep updated a risk or opportunity management strategy. | Risk or opportunity management strategy | High | Medium | All Organisations | All | Not Started
93 | 12 | Risk & Opportunity Management | RSK | Managing | L3 – Defined | RSK 3.4 — Develop and keep updated risk or opportunity management plans | Create mitigation and leverage plans for selected risks and opportunities. | Develop mitigation plans for selected risks and contingency plans. | Risk management plans | High | Medium | All Organisations | All | Not Started
94 | 12 | Risk & Opportunity Management | RSK | Managing | L3 – Defined | RSK 3.5 — Manage risks or opportunities by implementing planned activities | Execute risk and opportunity management plans. | Manage risks or opportunities using the management plans. | Updated status | High | Medium | All Organisations | All | Not Started
95 | 13 | Enabling Virtual Work | EVW | Enabling – People | L1 – Initial / Foundation | EVW 1.1 — Identify and record virtual work needs and constraints | Understand the needs and limitations of virtual/remote work. | Identify virtual work needs and constraints. | List of virtual work needs and constraints | Low | High | All Organisations | All | Not Started
96 | 13 | Enabling Virtual Work | EVW | Enabling – People | L1 – Initial / Foundation | EVW 1.2 — Perform virtual work | Carry out virtual work and communicate results. | Perform virtual work. | Outputs from virtual work | Low | High | All Organisations | All | Not Started
97 | 13 | Enabling Virtual Work | EVW | Enabling – People | L2 – Managed / Core | EVW 2.1 — Develop, keep updated, and use an approach to perform virtual work | Define and follow a systematic virtual work approach. | Develop and record an approach for virtual work and keep it updated. | Approach for virtual work solution delivery | Low | High | All Organisations | All | Not Started
98 | 13 | Enabling Virtual Work | EVW | Enabling – People | L2 – Managed / Core | EVW 2.2 — Monitor the virtual work approach and take corrective action when needed | Track and improve the virtual work approach. | Review virtual work according to the virtual work approach. | Revisions to the virtual work approach | Low | High | All Organisations | All | Not Started
99 | 13 | Enabling Virtual Work | EVW | Enabling – People | L3 – Defined | EVW 3.1 — Develop, keep updated, and use an organizational strategy for virtual work | Build organizational capability for effective virtual work. | Identify organizational strategy, roles, responsibilities, and tasks for virtual work. | Organizational virtual work strategy and approach | Low | Medium | All Organisations | All | Not Started
100 | 13 | Enabling Virtual Work | EVW | Enabling – People | L3 – Defined | EVW 3.2 — Perform reviews periodically on the effectiveness of the virtual work approach | Continuously improve the organization's virtual work approach. | Conduct periodic and as-needed virtual work reviews across the organization. | Virtual work review results | Low | Medium | All Organisations | All | Not Started
101 | 14 | Organizational Training | OT | Enabling – People | L1 – Initial / Foundation | OT 1.1 — Train people | Identify training needs, schedule, and deliver training. | Identify people who will receive the training. | Completed training records | Medium | High | All Organisations | All | Not Started
102 | 14 | Organizational Training | OT | Enabling – People | L2 – Managed / Core | OT 2.1 — Identify training needs | Identify skills and knowledge gaps and resulting training needs. | Identify skills and knowledge for each role. | List of training needs | Medium | High | All Organisations | All | Not Started
103 | 14 | Organizational Training | OT | Enabling – People | L2 – Managed / Core | OT 2.2 — Train personnel and keep records | Deliver training and maintain training records. | Deliver training based on identified training needs. | Records of delivered training | Medium | High | All Organisations | All | Not Started
104 | 14 | Organizational Training | OT | Enabling – People | L3 – Defined | OT 3.1 — Develop and keep updated the organization's strategic and short-term training needs | Identify and prioritize training needs across the organization. | Determine the roles and skills needed to perform the organization's standard processes. | Training needs | Medium | Medium | All Organisations | All | Not Started
105 | 14 | Organizational Training | OT | Enabling – People | L3 – Defined | OT 3.2 — Coordinate training needs and delivery between the projects and the organization | Align training delivery across projects and the organization. | Analyze the training needs identified by work and support groups. | Allocated training needs | Medium | Medium | All Organisations | All | Not Started
106 | 14 | Organizational Training | OT | Enabling – People | L3 – Defined | OT 3.3 — Develop, keep updated, and follow organizational training plans | Establish strategic and short-term training plans with commitments. | Develop the content of the organizational training strategic plan. | Organizational training strategic plan | Medium | Medium | All Organisations | All | Not Started
107 | 14 | Organizational Training | OT | Enabling – People | L3 – Defined | OT 3.4 — Develop, keep updated, and use a training capability to address organizational needs | Build and maintain organizational training capability. | Select approaches to satisfy organizational training needs. | Training materials and support artifacts | Medium | Medium | All Organisations | All | Not Started
108 | 14 | Organizational Training | OT | Enabling – People | L3 – Defined | OT 3.5 — Assess and report the effectiveness of the organization's training program | Evaluate and report on how well the training program is working. | Assess the effectiveness of each training course. | Training effectiveness surveys | Medium | Medium | All Organisations | All | Not Started
109 | 14 | Organizational Training | OT | Enabling – People | L3 – Defined | OT 3.6 — Record, keep updated, and use the set of organizational training records | Maintain comprehensive training records and make them available. | Keep and use records of all participants. | Training records and reports | Medium | Medium | All Organisations | All | Not Started
110 | 15 | Workforce Empowerment | WE | Enabling – People | L1 – Initial / Foundation | WE 1.1 — Identify and allocate commitments to workgroups | Match work commitments to skilled personnel in workgroups. | Develop a list of work commitments. | Work commitments and assignments | Low | High | All Organisations | Medium–Large | Not Started
111 | 15 | Workforce Empowerment | WE | Enabling – People | L2 – Managed / Core | WE 2.1 — Record and allocate work assignments based on qualifications and skills | Match individuals to work assignments using structured selection processes. | Analyze work commitments to determine the effort and skills required. | Work assignment selection strategy | Low | High | All Organisations | Medium–Large | Not Started
112 | 15 | Workforce Empowerment | WE | Enabling – People | L2 – Managed / Core | WE 2.2 — Manage the transition of individuals in and out of roles and workgroups | Handle personnel transitions in a planned and structured manner. | Plan for personnel transition activities. | Staff transition plans | Low | High | All Organisations | Medium–Large | Not Started
113 | 15 | Workforce Empowerment | WE | Enabling – People | L2 – Managed / Core | WE 2.3 — Develop, keep updated, and use communication and coordination mechanisms | Facilitate communication and coordination within and across workgroups. | Review work objectives with all affected workgroups. | Team norms, values, and charters | Low | High | All Organisations | Medium–Large | Not Started
114 | 15 | Workforce Empowerment | WE | Enabling – People | L3 – Defined | WE 3.1 — Develop, keep updated, and use workforce competencies to build organizational capabilities | Use workforce competency analysis to drive organizational capability improvement. | Identify knowledge, skills, process abilities, and performance expectations for each competency. | Workforce competency list and descriptions | Low | Medium | All Organisations | Medium–Large | Not Started
115 | 15 | Workforce Empowerment | WE | Enabling – People | L3 – Defined | WE 3.2 — Develop, keep updated, and use an organizational structure to empower workgroups | Delegate authority and accountability to workgroups effectively. | Determine and communicate delegation of authority to workgroups. | Recorded organizational delegations of authority, expectations for accountability, and negotiation results | Low | Medium | All Organisations | Medium–Large | Not Started
116 | 15 | Workforce Empowerment | WE | Enabling – People | L3 – Defined | WE 3.3 — Develop, keep updated, and use organizational compensation strategies | Design and maintain fair and effective compensation strategies. | Develop and use a compensation strategy and approach. | Recorded compensation strategy and approach | Low | Medium | All Organisations | Medium–Large | Not Started
117 | 16 | Estimating | EST | Managing | L1 – Initial / Foundation | EST 1.1 — Develop high-level estimates to perform the work | Produce rough-order-of-magnitude estimates for initial planning. | Review needs and assumptions and determine high-level estimates with stakeholders. | Rough order of magnitude estimates | High | High | All Organisations | All | Not Started
118 | 16 | Estimating | EST | Managing | L2 – Managed / Core | EST 2.1 — Develop, keep updated, and use the scope of what is being estimated | Define and maintain the scope of the estimating effort. | Review requirements and objectives with stakeholders to determine scope. | List of tasks and activities / Work Breakdown Structure (WBS) | High | High | All Organisations | All | Not Started
119 | 16 | Estimating | EST | Managing | L2 – Managed / Core | EST 2.2 — Develop and keep updated estimates for the size of the solution | Estimate the size and complexity of solutions and tasks. | Use applicable methods to estimate the size and complexity of solutions and tasks. | Size estimate | High | High | All Organisations | All | Not Started
120 | 16 | Estimating | EST | Managing | L2 – Managed / Core | EST 2.3 — Develop and record effort, duration, and cost estimates | Produce calibrated estimates with documented rationale. | Collect and use historical data to develop or calibrate estimation models. | Effort estimate | High | High | All Organisations | All | Not Started
121 | 16 | Estimating | EST | Managing | L3 – Defined | EST 3.1 — Develop and keep updated a recorded estimation method | Define a validated and calibrated estimation method. | Determine the acceptable estimation methods. | Recorded estimation method | High | Medium | All Organisations | All | Not Started
122 | 16 | Estimating | EST | Managing | L3 – Defined | EST 3.2 — Use the organizational measurement repository and process assets for estimating | Leverage organizational data and assets to improve estimation accuracy. | Use organizational assets and measures for estimation. | Work estimates | High | Medium | All Organisations | All | Not Started
123 | 17 | Monitor & Control | MC | Managing | L1 – Initial / Foundation | MC 1.1 — Record task completions | Track and record completion of project tasks. | Record task completion. | Task list | High | High | All Organisations | All | Not Started
124 | 17 | Monitor & Control | MC | Managing | L1 – Initial / Foundation | MC 1.2 — Identify and resolve issues | Track and resolve issues and action items. | Record the issue in the issue and action item list. | Issues and action item list | High | High | All Organisations | All | Not Started
125 | 17 | Monitor & Control | MC | Managing | L2 – Managed / Core | MC 2.1 — Track actual results against estimates | Monitor actuals vs. plans for size, effort, schedule, resources, and budget. | Track actual results to plans and estimates. | Records of actuals versus estimates | High | High | All Organisations | All | Not Started
126 | 17 | Monitor & Control | MC | Managing | L2 – Managed / Core | MC 2.2 — Track the involvement of identified stakeholders and commitments | Monitor stakeholder engagement and fulfillment of commitments. | Periodically review and record the status of stakeholder involvement. | Records of stakeholder involvement | High | High | All Organisations | All | Not Started
127 | 17 | Monitor & Control | MC | Managing | L2 – Managed / Core | MC 2.3 — Monitor the transition to operations and support | Track readiness to transition the solution to operations and support. | Monitor capabilities of operations and support to receive and use new solutions. | Status reports of transition | High | High | All Organisations | All | Not Started
128 | 17 | Monitor & Control | MC | Managing | L2 – Managed / Core | MC 2.4 — Take corrective actions when actual results differ significantly from plans | Address deviations from planned results through corrective actions. | Collect issues for analysis. | List of issues requiring corrective action | High | High | All Organisations | All | Not Started
129 | 17 | Monitor & Control | MC | Managing | L3 – Defined | MC 3.1 — Manage the project using the project plan and the project process | Use the project process and plans to manage project activities. | Manage project activities using the project process and all related plans. | Results of monitoring | High | Medium | All Organisations | All | Not Started
130 | 17 | Monitor & Control | MC | Managing | L3 – Defined | MC 3.2 — Manage critical dependencies and activities | Track and manage critical project dependencies. | Review and update dependencies. | Updated critical dependencies | High | Medium | All Organisations | All | Not Started
131 | 17 | Monitor & Control | MC | Managing | L3 – Defined | MC 3.3 — Monitor the work environment to identify issues | Track the work environment for factors that impact performance. | Monitor work environment elements that affect safety, health, effectiveness, and productivity. | Corrections needed to the work environment | High | Medium | All Organisations | All | Not Started
132 | 17 | Monitor & Control | MC | Managing | L3 – Defined | MC 3.4 — Manage and resolve issues with affected stakeholders | Escalate and resolve issues with affected stakeholders. | Identify and record issues. | Recorded issues | High | Medium | All Organisations | All | Not Started
133 | 18 | Planning | PLAN | Managing | L1 – Initial / Foundation | PLAN 1.1 — Develop a list of tasks | Create and review a basic list of project tasks. | Develop a task list. | Task list | High | High | All Organisations | All | Not Started
134 | 18 | Planning | PLAN | Managing | L1 – Initial / Foundation | PLAN 1.2 — Assign people to tasks | Allocate responsibilities for each task. | Assign an individual who is responsible for each task. | Task list with assignments | High | High | All Organisations | All | Not Started
135 | 18 | Planning | PLAN | Managing | L2 – Managed / Core | PLAN 2.1 — Develop and keep updated the approach for accomplishing the work | Define the overall approach and lifecycle for the project. | Identify the objectives of the project. | Recorded approach for accomplishing the objectives | High | High | All Organisations | All | Not Started
136 | 18 | Planning | PLAN | Managing | L2 – Managed / Core | PLAN 2.2 — Plan for the knowledge and skills needed to perform the work | Identify knowledge and skills gaps and select methods to fill them. | Identify the knowledge and skills needed to perform the work. | Inventory of skill needs | High | High | All Organisations | All | Not Started
137 | 18 | Planning | PLAN | Managing | L2 – Managed / Core | PLAN 2.3 — Develop and keep the budget and schedule updated | Create and maintain a realistic budget and schedule based on estimates. | Identify major milestones. | Budget | High | High | All Organisations | All | Not Started
138 | 18 | Planning | PLAN | Managing | L2 – Managed / Core | PLAN 2.4 — Plan the involvement of identified stakeholders | Define how stakeholders will be involved and communicated with. | Develop a list of stakeholders. | Stakeholder involvement plan | High | High | All Organisations | All | Not Started
139 | 18 | Planning | PLAN | Managing | L2 – Managed / Core | PLAN 2.5 — Plan transition to operations and support | Define how the solution will be transitioned to operations. | Determine transition scope and objectives. | Plans for transition to operations and support | High | High | All Organisations | All | Not Started
140 | 18 | Planning | PLAN | Managing | L2 – Managed / Core | PLAN 2.6 — Ensure plans are feasible by reconciling estimates against resource capacity | Validate that plans are achievable given available resources. | Identify and plan for resource capacity and availability. | Revised plan and commitments | High | High | All Organisations | All | Not Started
141 | 18 | Planning | PLAN | Managing | L2 – Managed / Core | PLAN 2.7 — Develop the project plan, ensure consistency, and keep it updated | Integrate all plan elements into a coherent project plan. | Record the project plan. | Overall project plans | High | High | All Organisations | All | Not Started
142 | 18 | Planning | PLAN | Managing | L2 – Managed / Core | PLAN 2.8 — Review plans and obtain commitments from affected stakeholders | Get buy-in and formal commitments from stakeholders on the plan. | Ensure individuals are involved in reviewing work they are responsible for. | Results of plan reviews | High | High | All Organisations | All | Not Started
143 | 18 | Planning | PLAN | Managing | L3 – Defined | PLAN 3.1 — Use the organization's standard processes and tailoring guidelines to develop the project process | Tailor organizational processes for the project. | Select standard processes that best fit the project needs. | The project process | High | Medium | All Organisations | All | Not Started
144 | 18 | Planning | PLAN | Managing | L3 – Defined | PLAN 3.2 — Develop a plan using the project process, organizational process assets, and measurement repository | Create detailed project plans leveraging organizational assets and data. | Use tasks and work products of the project process as a basis for estimating. | Revised project estimates | High | Medium | All Organisations | All | Not Started
145 | 18 | Planning | PLAN | Managing | L3 – Defined | PLAN 3.3 — Identify and negotiate critical dependencies | Manage critical inter-project or inter-team dependencies. | Identify each critical dependency. | Critical dependencies | High | Medium | All Organisations | All | Not Started
146 | 18 | Planning | PLAN | Managing | L3 – Defined | PLAN 3.4 — Plan for the project environment | Plan resources, facilities, and environment needed for the project. | Analyze project and plan for resources, facilities, and environment. | Project resources, facilities, and environment plan | High | Medium | All Organisations | All | Not Started
147 | 18 | Planning | PLAN | Managing | L4 – Quantitatively Managed | PLAN 4.1 — Use statistical and quantitative techniques to develop and keep project processes updated | Select project processes quantitatively to achieve QPPOs. | Develop the criteria to use in evaluating process alternatives for the project. | Criteria used to evaluate alternatives | High | Low | All Organisations | All | Not Started
148 | 19 | Data Management | DM | Enabling – Data | L1 – Initial / Foundation | DM 1.1 — Identify data management objectives | Define priorities and objectives for managing data. | Identify data management objectives and priorities. | Recorded data management objectives | Medium | High | All Organisations | All | Not Started
149 | 19 | Data Management | DM | Enabling – Data | L1 – Initial / Foundation | DM 1.2 — Use metadata to manage data | Define and use metadata to support data management. | Define, record, and use metadata. | Metadata repositories | Medium | High | All Organisations | All | Not Started
150 | 19 | Data Management | DM | Enabling – Data | L2 – Managed / Core | DM 2.1 — Develop, keep updated, and follow a data management approach | Establish and maintain a data management approach aligned to objectives. | Periodically review and update data management objectives. | Data management objectives | Medium | High | All Organisations | All | Not Started
151 | 19 | Data Management | DM | Enabling – Data | L2 – Managed / Core | DM 2.2 — Establish a data management architecture | Design and implement architecture to support the data management approach. | Design the data architecture consistent with requirements. | Meeting notes or review results from stakeholders | Medium | High | All Organisations | All | Not Started
152 | 19 | Data Management | DM | Enabling – Data | L3 – Defined | DM 3.1 — Establish and deploy an organizational data management capability | Build and maintain an organizational data management function. | Identify approach, roles, responsibilities, and tasks for operating the data management function. | Organizational data management approach | Medium | Medium | All Organisations | All | Not Started
153 | 19 | Data Management | DM | Enabling – Data | L3 – Defined | DM 3.2 — Perform periodic reviews on the effectiveness of the organization's data management capability | Continuously improve organizational data management practices. | Review industry standards, trends, and emerging technologies in data management. | Industry research report for data management | Medium | Medium | All Organisations | All | Not Started
154 | 20 | Data Quality | DQ | Enabling – Data | L1 – Initial / Foundation | DQ 1.1 — Identify data quality parameters | Define the data quality parameters important to the business. | Define data quality parameters important to the business. | Defined data quality parameters | Medium | High | All Organisations | All | Not Started
155 | 20 | Data Quality | DQ | Enabling – Data | L1 – Initial / Foundation | DQ 1.2 — Perform data cleansing activities | Review and cleanse data to improve quality. | Review and cleanse data. | Results of data cleansing activities | Medium | High | All Organisations | All | Not Started
156 | 20 | Data Quality | DQ | Enabling – Data | L2 – Managed / Core | DQ 2.1 — Define criteria for data cleansing | Establish and maintain criteria for determining when data needs cleansing. | Identify criteria for data cleansing. | List of data cleansing criteria | Medium | High | All Organisations | All | Not Started
157 | 20 | Data Quality | DQ | Enabling – Data | L2 – Managed / Core | DQ 2.2 — Develop, keep updated, and follow a data quality approach | Establish and follow a documented data quality approach. | Develop a data quality approach. | Data quality approach | Medium | High | All Organisations | All | Not Started
158 | 20 | Data Quality | DQ | Enabling – Data | L2 – Managed / Core | DQ 2.3 — Perform data cleansing based on criteria and data quality approach | Execute data cleansing activities following the defined approach. | Perform data cleansing. | Log of data corrections | Medium | High | All Organisations | All | Not Started
159 | 20 | Data Quality | DQ | Enabling – Data | L3 – Defined | DQ 3.1 — Conduct data quality assessments | Systematically assess data quality and plan remediation. | Establish, review, and update data profiles. | Data profiling reports | Medium | Medium | All Organisations | All | Not Started
160 | 20 | Data Quality | DQ | Enabling – Data | L3 – Defined | DQ 3.2 — Perform periodic reviews on the effectiveness of data quality activities | Continuously improve data quality practices. | Review industry standards, trends, and emerging technologies in data quality. | Analysis results | Medium | Medium | All Organisations | All | Not Started
161 | 21 | Enabling Safety | ESAF | Enabling – Safety & Security | L1 – Initial / Foundation | ESAF 1.1 — Identify and record safety needs and hazards | Identify current and potential safety hazards and improvement opportunities. | Identify and record current and potential safety hazards and improvements. | List of identified hazards and improvements | Low | High | Safety-Critical / Manufacturing / Regulated | All | Not Started
162 | 21 | Enabling Safety | ESAF | Enabling – Safety & Security | L1 – Initial / Foundation | ESAF 1.2 — Address prioritized safety needs and hazards | Prioritize and create action plans to address safety hazards. | Assess and determine the potential consequences of hazards and improvements. | Hazard logs | Low | High | Safety-Critical / Manufacturing / Regulated | All | Not Started
163 | 21 | Enabling Safety | ESAF | Enabling – Safety & Security | L2 – Managed / Core | ESAF 2.1 — Identify critical safety needs and constraints, develop safety objectives | Define safety vision, objectives, and action plans. | Define safety objectives. | Safety vision | Low | High | Safety-Critical / Manufacturing / Regulated | All | Not Started
164 | 21 | Enabling Safety | ESAF | Enabling – Safety & Security | L2 – Managed / Core | ESAF 2.2 — Develop, keep updated, and follow an approach to address workplace environment safety | Address workplace environment safety systematically. | Identify workplace environment safety requirements. | Workplace environment requirements | Low | High | Safety-Critical / Manufacturing / Regulated | All | Not Started
165 | 21 | Enabling Safety | ESAF | Enabling – Safety & Security | L2 – Managed / Core | ESAF 2.3 — Develop, keep updated, and follow an approach to address functional safety for the solution | Address functional safety of the product/solution. | Identify functional safety requirements. | Functional safety requirements | Low | High | Safety-Critical / Manufacturing / Regulated | All | Not Started
166 | 21 | Enabling Safety | ESAF | Enabling – Safety & Security | L3 – Defined | ESAF 3.1 — Establish and deploy an organizational safety capability | Build and maintain organizational safety capability. | Define safety awareness, knowledge, roles, and skills. | Safety roles, skills, and training matrix | Low | Medium | Safety-Critical / Manufacturing / Regulated | All | Not Started
167 | 21 | Enabling Safety | ESAF | Enabling – Safety & Security | L3 – Defined | ESAF 3.2 — Perform safety evaluations periodically and take action on results | Evaluate safety programs and activities on a periodic basis. | Collect information and conduct analysis from identified potential or current hazards. | List of in-service failures | Low | Medium | Safety-Critical / Manufacturing / Regulated | All | Not Started
168 | 21 | Enabling Safety | ESAF | Enabling – Safety & Security | L3 – Defined | ESAF 3.3 — Develop, keep updated, and follow organizational safety control strategies | Establish and execute systematic safety control strategies. | Establish hierarchy of safety controls. | Safety control strategies | Low | Medium | Safety-Critical / Manufacturing / Regulated | All | Not Started
169 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L1 – Initial / Foundation | ESEC 1.1 — Identify and record security needs and issues | Identify and record security needs and issues for the work. | Identify security needs and issues associated with the work. | List of security issues and impacts | High | High | All Organisations | All | Not Started
170 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L1 – Initial / Foundation | ESEC 1.2 — Address prioritized security needs and issues | Prioritize and resolve security issues. | Review, prioritize, and record security issues and keep them updated. | Security action plans | High | High | All Organisations | All | Not Started
171 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L2 – Managed / Core | ESEC 2.1 — Identify and record security needs, develop a security approach and objectives | Establish security objectives and a systematic security approach. | Define, record, and keep security objectives updated for the work. | Documentation of security objectives for data and functions and associated levels of impact | High | High | All Organisations | All | Not Started
172 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L2 – Managed / Core | ESEC 2.2 — Develop, keep updated, and follow an approach to address physical security needs | Address physical security using a defense-in-depth approach. | Identify, record, and keep an approach to address physical security needs updated. | Recorded physical security approach | High | High | All Organisations | All | Not Started
173 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L2 – Managed / Core | ESEC 2.3 — Develop, keep updated, and follow an approach to address mission, personnel, and process-related security needs | Address mission, personnel, and process security using a defense-in-depth approach. | Identify, record, and keep an approach to address mission, personnel, and process needs updated. | Recorded mission, personnel, and process security approach | High | High | All Organisations | All | Not Started
174 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L2 – Managed / Core | ESEC 2.4 — Develop, keep updated, and follow an approach to address cybersecurity needs | Address cybersecurity using a defense-in-depth approach. | Identify, record, and keep an approach updated to address cybersecurity needs. | Recorded and updated cybersecurity approach | High | High | All Organisations | All | Not Started
175 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L3 – Defined | ESEC 3.1 — Establish and deploy an organizational security operations capability | Build and maintain organizational security operations. | Identify approach, roles, responsibilities, and tasks for operating the security function. | Security operations approach and plans | High | Medium | All Organisations | All | Not Started
176 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L3 – Defined | ESEC 3.2 — Develop, follow, and implement an organizational security strategy, approach, and architecture | Define and maintain an organization-wide security strategy and architecture. | Identify organizational security architecture needs. | Recorded security strategy and approach | High | Medium | All Organisations | All | Not Started
177 | 22 | Enabling Security | ESEC | Enabling – Safety & Security | L3 – Defined | ESEC 3.3 — Periodically perform security reviews and evaluations and take action on results | Continuously evaluate and improve organizational security. | Conduct periodic or as-needed security reviews and evaluations. | Security review results | High | Medium | All Organisations | All | Not Started
178 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L1 – Initial / Foundation | MST 1.1 — Identify and record security threats and vulnerabilities | Capture all identified security threats and vulnerabilities. | Identify security threats and vulnerabilities. | List of identified security threats and vulnerabilities | Medium | High | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
179 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L1 – Initial / Foundation | MST 1.2 — Take actions to address security threats and vulnerabilities | Take steps to remediate identified threats and vulnerabilities. | Take steps or actions to address identified security threats and vulnerabilities. | Recorded steps or actions addressing threats and vulnerabilities | Medium | High | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
180 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L2 – Managed / Core | MST 2.1 — Develop, keep updated, and follow an approach for handling security threats and vulnerabilities | Establish a risk-based approach for managing threats and vulnerabilities. | Identify techniques for handling threats and vulnerabilities. | Recorded risk-based approach for handling security threats and vulnerabilities | Medium | High | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
181 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L2 – Managed / Core | MST 2.2 — Develop and keep updated criteria to evaluate security threats and vulnerabilities | Define consistent evaluation criteria for threats and vulnerabilities. | Define and record criteria for consistently evaluating threats, vulnerabilities, and incidents. | Criteria for evaluation of threats and vulnerabilities | Medium | High | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
182 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L2 – Managed / Core | MST 2.3 — Use recorded criteria to prioritize, monitor, and address critical security threats | Apply criteria to prioritize and track security threats and vulnerabilities. | Use recorded criteria to prioritize security threats and vulnerabilities. | Recorded list of prioritized threats and vulnerabilities | Medium | High | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
183 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L2 – Managed / Core | MST 2.4 — Evaluate and report the effectiveness of the approach and actions taken | Assess whether threat and vulnerability handling actions are effective. | Identify and develop comprehensive evaluation techniques. | Recorded evaluation approaches and techniques | Medium | High | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
184 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L3 – Defined | MST 3.1 — Develop, keep updated, and follow an organizational security strategy, approach, and architecture | Define organizational security strategy and architecture and verify threats/vulnerabilities. | Define the organizational security strategy, approach, and architecture. | System Security Plan (SSP) | Medium | Medium | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
185 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L3 – Defined | MST 3.2 — Analyze security verification and validation results | Consolidate and analyse VV results across the organization. | Consolidate the results of security verification and validation activities. | Consolidated security verification and validation results | Medium | Medium | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
186 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L3 – Defined | MST 3.3 — Evaluate effectiveness of the organizational security strategy, approach, and architecture | Assess whether the organizational security strategy effectively addresses threats. | Define evaluation criteria. | Results of strategy, approach, and architecture evaluation effectiveness | Medium | Medium | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
187 | 23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | L4 – Quantitatively Managed | MST 4.1 — Employ threat intelligence analysis using statistical and quantitative techniques | Use threat intelligence data and quantitative analysis to improve security. | Identify, record, and keep threat intelligence analysis requirements updated. | Current threat intelligence requirements | Medium | Low | IT / Cybersecurity-Focused Orgs | Medium–Large | Not Started
188 | 24 | Causal Analysis & Resolution | CAR | Improving | L1 – Initial / Foundation | CAR 1.1 — Identify and address causes of selected outcomes | Investigate causes of unexpected outcomes and take corrective action. | Select outcomes that differed from expectation. | List of investigated outcomes | Medium | High | All Organisations | All | Not Started
189 | 24 | Causal Analysis & Resolution | CAR | Improving | L2 – Managed / Core | CAR 2.1 — Select outcomes for analysis | Decide which outcomes warrant deeper causal analysis. | Define the scope of the analysis. | Analysis results | Medium | High | All Organisations | All | Not Started
190 | 24 | Causal Analysis & Resolution | CAR | Improving | L2 – Managed / Core | CAR 2.2 — Analyze and address causes of outcomes | Perform causal analysis and implement corrective actions. | Identify the affected stakeholders and involve them. | List of affected stakeholders | Medium | High | All Organisations | All | Not Started
191 | 24 | Causal Analysis & Resolution | CAR | Improving | L3 – Defined | CAR 3.1 — Determine causes of selected outcomes by following an organizational process | Use an organizational process to systematically identify root causes. | Identify and involve stakeholders. | List of causes | Medium | Medium | All Organisations | All | Not Started
192 | 24 | Causal Analysis & Resolution | CAR | Improving | L3 – Defined | CAR 3.2 — Propose actions to address identified causes | Develop action proposals to address identified causes. | Develop an action proposal. | Action proposals | Medium | Medium | All Organisations | All | Not Started
193 | 24 | Causal Analysis & Resolution | CAR | Improving | L3 – Defined | CAR 3.3 — Implement selected action proposals | Prioritize, select, and implement action proposals. | Analyze action proposals and determine their priorities. | Action proposals selected for implementation | Medium | Medium | All Organisations | All | Not Started
194 | 24 | Causal Analysis & Resolution | CAR | Improving | L3 – Defined | CAR 3.4 — Record causal analysis and resolution data | Maintain records of causal analysis and resolutions. | Record causal analysis data and make the data available for use. | Cause analysis and resolution records | Medium | Medium | All Organisations | All | Not Started
195 | 24 | Causal Analysis & Resolution | CAR | Improving | L3 – Defined | CAR 3.5 — Submit improvement proposals for changes proven to be effective | Promote effective resolutions as organizational improvement proposals. | Submit improvement proposals. | Improvement proposals | Medium | Medium | All Organisations | All | Not Started
196 | 24 | Causal Analysis & Resolution | CAR | Improving | L4 – Quantitatively Managed | CAR 4.1 — Perform root cause analysis using statistical and quantitative techniques | Apply statistical techniques to identify and address root causes. | Perform root cause analysis. | Process and project performance analyses | Medium | Low | All Organisations | All | Not Started
197 | 24 | Causal Analysis & Resolution | CAR | Improving | L4 – Quantitatively Managed | CAR 4.2 — Evaluate the effect of implemented actions on process performance using statistical techniques | Measure the impact of corrective actions on process performance. | Measure and analyze the change in process performance. | Analysis of change in process performance | Medium | Low | All Organisations | All | Not Started
198 | 24 | Causal Analysis & Resolution | CAR | Improving | L5 – Optimising | CAR 5.1 — Use statistical and quantitative techniques to evaluate solutions and processes to optimize performance | Apply improvements across the organization for performance optimization. | Identify similar processes or solutions. | Identified candidate processes and solutions | Medium | Low | All Organisations | All | Not Started
199 | 25 | Configuration Management | CM | Supporting | L1 – Initial / Foundation | CM 1.1 — Perform version control | Maintain version control over designated work products. | List the work products to be placed under version control and keep it updated. | List of work products and versions | High | High | Software / Systems Dev / IT Operations | All | Not Started
200 | 25 | Configuration Management | CM | Supporting | L2 – Managed / Core | CM 2.1 — Identify items to be placed under configuration management | Define and identify configuration items. | Assign unique identifiers to configuration items. | Identified configuration items | High | High | Software / Systems Dev / IT Operations | All | Not Started
201 | 25 | Configuration Management | CM | Supporting | L2 – Managed / Core | CM 2.2 — Develop, keep updated, and use a configuration and change management system | Establish a system to control, track, and manage configuration items. | Describe how items and changes are controlled, used, and managed. | Configuration management system | High | High | Software / Systems Dev / IT Operations | All | Not Started
202 | 25 | Configuration Management | CM | Supporting | L2 – Managed / Core | CM 2.3 — Develop or release baselines for internal use or delivery to the customer | Create and maintain formal baselines for configuration items. | Obtain authorization before developing or releasing baselines. | Authorization | High | High | Software / Systems Dev / IT Operations | All | Not Started
203 | 25 | Configuration Management | CM | Supporting | L2 – Managed / Core | CM 2.4 — Manage changes to items under configuration management | Control changes to configuration items using a formal change process. | Initiate and record change requests. | Change requests | High | High | Software / Systems Dev / IT Operations | All | Not Started
204 | 25 | Configuration Management | CM | Supporting | L2 – Managed / Core | CM 2.5 — Develop, keep updated, and use records describing items under configuration management | Maintain accurate status and history records for configuration items. | Record configuration management actions in sufficient detail. | Revision history or change log of configuration items | High | High | Software / Systems Dev / IT Operations | All | Not Started
205 | 25 | Configuration Management | CM | Supporting | L2 – Managed / Core | CM 2.6 — Perform configuration audits to maintain the integrity of baselines | Conduct configuration audits to verify integrity of baselines and records. | Assess the integrity of baselines and generate action items. | Configuration audit or review results | High | High | Software / Systems Dev / IT Operations | All | Not Started
206 | 26 | Decision Analysis & Resolution | DAR | Supporting | L1 – Initial / Foundation | DAR 1.1 — Define and record the alternatives | Capture decision alternatives with stakeholder involvement. | Define the alternatives. | Statement of the alternatives | Low | High | All Organisations | All | Not Started
207 | 26 | Decision Analysis & Resolution | DAR | Supporting | L1 – Initial / Foundation | DAR 1.2 — Make and record the decision | Make and formally record the decision. | Make and record the decision. | Recorded decisions | Low | High | All Organisations | All | Not Started
208 | 26 | Decision Analysis & Resolution | DAR | Supporting | L2 – Managed / Core | DAR 2.1 — Develop, keep updated, and use rules to determine when to follow a criteria-based decision process | Establish guidelines for when formal decision analysis is required. | Develop and record rules and guidelines for when to use a criteria-based decision process. | Rules and guidelines for criteria-based decision-making | Low | High | All Organisations | All | Not Started
209 | 26 | Decision Analysis & Resolution | DAR | Supporting | L2 – Managed / Core | DAR 2.2 — Develop criteria for evaluating alternatives | Define weighted criteria for comparing decision alternatives. | Define the criteria for evaluating alternative solutions. | Recorded evaluation criteria | Low | High | All Organisations | All | Not Started
210 | 26 | Decision Analysis & Resolution | DAR | Supporting | L2 – Managed / Core | DAR 2.3 — Identify alternative solutions | Research and identify additional decision alternatives. | Research information about similar internal or external past decisions. | Recorded alternatives | Low | High | All Organisations | All | Not Started
211 | 26 | Decision Analysis & Resolution | DAR | Supporting | L2 – Managed / Core | DAR 2.4 — Select evaluation methods | Choose appropriate methods for evaluating alternatives. | Select evaluation methods. | Selected evaluation methods | Low | High | All Organisations | All | Not Started
212 | 26 | Decision Analysis & Resolution | DAR | Supporting | L2 – Managed / Core | DAR 2.5 — Evaluate and select solutions using criteria and methods | Apply criteria and methods to select the recommended solution. | Evaluate proposed alternative solutions following the recorded process. | Evaluation results | Low | High | All Organisations | All | Not Started
213 | 26 | Decision Analysis & Resolution | DAR | Supporting | L3 – Defined | DAR 3.1 — Develop, keep updated, and use a description of role-based decision authority | Define and communicate decision-making authority by role. | Identify, record, keep updated, and communicate roles and levels of decision-making authority. | List of roles and decision authority and responsibilities | Low | Medium | All Organisations | All | Not Started
214 | 27 | Managing Performance & Measurement | MPM | Improving | L1 – Initial / Foundation | MPM 1.1 — Collect measures and record performance | Gather and record measures to understand performance. | Identify available measures and collection methods. | Measures | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
215 | 27 | Managing Performance & Measurement | MPM | Improving | L1 – Initial / Foundation | MPM 1.2 — Identify and address performance issues | Review performance and address identified issues. | Collect measurements and derive performance data. | List of performance issues | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
216 | 27 | Managing Performance & Measurement | MPM | Improving | L2 – Managed / Core | MPM 2.1 — Derive and record measurement and performance objectives from business needs | Establish measurement objectives aligned with business needs. | Identify current or planned performance improvements. | Measurement and performance objectives | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
217 | 27 | Managing Performance & Measurement | MPM | Improving | L2 – Managed / Core | MPM 2.2 — Develop, keep updated, and use operational definitions for measures | Define measures with clear operational definitions and collection methods. | Identify existing measures that address measurement objectives. | Operational definitions of measures | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
218 | 27 | Managing Performance & Measurement | MPM | Improving | L2 – Managed / Core | MPM 2.3 — Obtain specified measurement data according to the operational definitions | Collect and verify measurement data. | Collect data for currently specified base measures. | Base and derived measure data | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
219 | 27 | Managing Performance & Measurement | MPM | Improving | L2 – Managed / Core | MPM 2.4 — Analyze performance and measurement data | Analyse measurement data and draw conclusions. | Perform analyses, interpret results as planned, and draw conclusions. | Performance data analysis | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
220 | 27 | Managing Performance & Measurement | MPM | Improving | L2 – Managed / Core | MPM 2.5 — Store measurement data, specifications, and analysis results | Maintain measurement data and results in accordance with operational definitions. | Review data to ensure their quality. | Stored data | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
221 | 27 | Managing Performance & Measurement | MPM | Improving | L2 – Managed / Core | MPM 2.6 — Take actions to address identified issues with meeting measurement and performance objectives | Address deviations from measurement and performance objectives. | Record and implement corrective actions and manage to closure. | Revised objectives, plans, and commitments | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
222 | 27 | Managing Performance & Measurement | MPM | Improving | L3 – Defined | MPM 3.1 — Develop, keep updated, and use organizational measurement and performance objectives | Link organizational measurement objectives to business objectives. | Develop and analyze business objectives that drive measurement and performance objectives. | Business objectives | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
223 | 27 | Managing Performance & Measurement | MPM | Improving | L3 – Defined | MPM 3.2 — Follow organizational processes and standards to develop and use operational definitions for measures | Align measure definitions with organizational standards. | Record, communicate, and use organizational standard operational definitions. | Operational definitions for organizational standards | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
224 | 27 | Managing Performance & Measurement | MPM | Improving | L3 – Defined | MPM 3.3 — Develop, keep updated, and follow a data quality process | Ensure the quality, accuracy, and validity of measurement data. | Develop criteria for data quality, accuracy, precision, and validity. | Data quality criteria | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
225 | 27 | Managing Performance & Measurement | MPM | Improving | L3 – Defined | MPM 3.4 — Develop, keep updated, and use the organization's measurement repository | Build and maintain an organizational measurement repository. | Determine the organization's needs for storing, retrieving, and analysing measurements. | Measurement repository design | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
226 | 27 | Managing Performance & Measurement | MPM | Improving | L3 – Defined | MPM 3.5 — Analyze organizational performance to determine and address performance improvement needs | Use performance data to identify organizational improvement needs. | Aggregate performance data to the organizational level. | Aggregated performance data | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
227 | 27 | Managing Performance & Measurement | MPM | Improving | L3 – Defined | MPM 3.6 — Periodically communicate performance results to the organization | Report performance results to organizational stakeholders. | Develop and record performance improvement reports. | Performance improvement analysis reports | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
228 | 27 | Managing Performance & Measurement | MPM | Improving | L4 – Quantitatively Managed | MPM 4.1 — Use statistical and quantitative techniques to develop QPPOs | Establish QPPOs traceable to business objectives using quantitative methods. | Define, record, keep updated, and communicate QPPOs. | Quality and Process Performance Objectives (QPPOs) | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
229 | 27 | Managing Performance & Measurement | MPM | Improving | L4 – Quantitatively Managed | MPM 4.2 — Select measures and analytic techniques to quantitatively manage performance | Choose measures and techniques to achieve QPPOs. | Identify common measures from organizational repositories. | List of selected and new measures | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
230 | 27 | Managing Performance & Measurement | MPM | Improving | L4 – Quantitatively Managed | MPM 4.3 — Use statistical techniques to develop and analyze process performance baselines | Establish and maintain quantitative process performance baselines. | Analyze collected measures to establish central tendency and distribution. | Results of analysis of process performance data | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
231 | 27 | Managing Performance & Measurement | MPM | Improving | L4 – Quantitatively Managed | MPM 4.4 — Use statistical techniques to develop and analyze process performance models | Create and maintain quantitative process performance models. | Establish process performance models. | Process performance models | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
232 | 27 | Managing Performance & Measurement | MPM | Improving | L4 – Quantitatively Managed | MPM 4.5 — Use statistical techniques to determine achievement of QPPOs | Predict and manage achievement of QPPOs using quantitative methods. | Analyze the variation and stability of selected processes. | Results of analysis, validation, and calibration | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
233 | 27 | Managing Performance & Measurement | MPM | Improving | L5 – Optimising | MPM 5.1 — Use statistical techniques to align business objectives with business strategy | Optimize performance by ensuring business objectives align with strategy. | Evaluate and update business objectives to ensure alignment with business strategies. | Results of analysis of current performance against QPPOs, business objectives, and strategies | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
234 | 27 | Managing Performance & Measurement | MPM | Improving | L5 – Optimising | MPM 5.2 — Analyze performance data to determine ability to satisfy business objectives | Identify performance shortfalls and improvement opportunities. | Compare QPPOs to current process performance baselines and models. | Performance analysis results | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
235 | 27 | Managing Performance & Measurement | MPM | Improving | L5 – Optimising | MPM 5.3 — Select and implement improvement proposals based on quantitative analysis | Deploy performance improvements validated through quantitative analysis. | Run pilots to determine preliminary process performance. | Analysis of potential impacts of proposed improvements | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
236 | 28 | Process Asset Development | PAD | Improving | L1 – Initial / Foundation | PAD 1.1 — Develop process assets to perform the work | Create work instructions, templates, and process descriptions. | Record work instructions. | Work instructions | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
237 | 28 | Process Asset Development | PAD | Improving | L2 – Managed / Core | PAD 2.1 — Determine what process assets will be needed to perform the work | Identify the process assets required for project execution. | Identify process assets needed for the project. | Templates | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
238 | 28 | Process Asset Development | PAD | Improving | L2 – Managed / Core | PAD 2.2 — Develop, buy, or reuse process assets | Obtain process assets through build, buy, or reuse analysis. | Select which assets will be subject to a build, buy, or reuse analysis. | Build, buy, reuse analyses | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
239 | 28 | Process Asset Development | PAD | Improving | L2 – Managed / Core | PAD 2.3 — Make processes and assets available | Communicate and provide process assets to project teams. | Make assets available for use by projects. | Process assets | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
240 | 28 | Process Asset Development | PAD | Improving | L3 – Defined | PAD 3.1 — Develop, keep updated, and follow a strategy for building and updating process assets | Establish and maintain a strategy for developing process assets. | Develop a strategy for building and updating process assets. | Strategy for building and updating process assets | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
241 | 28 | Process Asset Development | PAD | Improving | L3 – Defined | PAD 3.2 — Develop, record, and keep updated a process architecture | Define the structure of the organization's processes and process assets. | Identify process requirements. | Process requirements | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
242 | 28 | Process Asset Development | PAD | Improving | L3 – Defined | PAD 3.3 — Develop, keep updated, and make the organization's processes and assets available | Establish and maintain the Process Asset Library (PAL). | Verify that the organization's standard processes and assets are aligned with strategic needs. | Design of the organization's PAL | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
243 | 28 | Process Asset Development | PAD | Improving | L3 – Defined | PAD 3.4 — Develop, keep updated, and use tailoring criteria and guidelines | Provide guidelines for tailoring standard processes to project needs. | Specify selection criteria and procedures for tailoring standard processes. | Tailoring guidelines for the organization's set of standard processes | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
244 | 28 | Process Asset Development | PAD | Improving | L3 – Defined | PAD 3.5 — Develop, keep updated, and make work environment standards available | Establish and maintain work environment standards for projects. | Evaluate commercially available work environment standards. | Work environment standards | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
245 | 28 | Process Asset Development | PAD | Improving | L3 – Defined | PAD 3.6 — Develop, keep updated, and make organizational measurement and analysis standards available | Standardize measurement and analysis practices across the organization. | Specify organizational standards for measurement and analysis. | Organizational measurement and analysis standards | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
246 | 29 | Process Management | PCM | Improving | L1 – Initial / Foundation | PCM 1.1 — Develop a support structure for process guidance and improvement | Establish roles and responsibilities for supporting process activities. | Identify and apply a structure for supporting process related activities. | Process support structure | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
247 | 29 | Process Management | PCM | Improving | L1 – Initial / Foundation | PCM 1.2 — Appraise the current process implementation and identify strengths and weaknesses | Conduct an appraisal to understand the current state of process implementation. | Obtain sponsorship and support from senior management. | Appraisal plan and schedule | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
248 | 29 | Process Management | PCM | Improving | L1 – Initial / Foundation | PCM 1.3 — Address improvement opportunities or process issues | Take action on identified process improvement opportunities and issues. | Assign relevant personnel to address improvement opportunities. | Action items | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
249 | 29 | Process Management | PCM | Improving | L2 – Managed / Core | PCM 2.1 — Identify improvements to the processes and process assets | Identify, prioritize, and select process improvements. | Identify issues and opportunities. | Proposed improvement list | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
250 | 29 | Process Management | PCM | Improving | L2 – Managed / Core | PCM 2.2 — Develop, keep updated, and follow plans for implementing selected process improvements | Plan, pilot, and deploy selected process improvements. | Select performance improvements to be deployed. | Process improvement plans | Medium | High | All Organisations (ML3+) | Medium–Large | Not Started
251 | 29 | Process Management | PCM | Improving | L3 – Defined | PCM 3.1 — Develop, keep updated, and use process improvement objectives traceable to business objectives | Link process improvement objectives to business objectives. | Identify and record improvement objectives. | Process improvement objectives traced to business objectives | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
252 | 29 | Process Management | PCM | Improving | L3 – Defined | PCM 3.2 — Identify processes that are the largest contributors to meeting business objectives | Determine which processes most strongly contribute to achieving business objectives. | Review the current business model, objectives, and environment. | Business model, objectives, and environment review results | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
253 | 29 | Process Management | PCM | Improving | L3 – Defined | PCM 3.3 — Explore and evaluate potential new processes, techniques, methods, and tools | Research and assess new processes and tools for improvement potential. | Identify, research, and record improvements. | Potential improvement opportunities | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
254 | 29 | Process Management | PCM | Improving | L3 – Defined | PCM 3.4 — Provide support for implementing, deploying, and sustaining process improvements | Ensure process improvements are successfully deployed and sustained. | Identify the mechanisms needed to support process implementation and deployment. | Plan for implementing, deploying, and sustaining improvements | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
255 | 29 | Process Management | PCM | Improving | L3 – Defined | PCM 3.5 — Deploy organizational standard processes and process assets | Roll out standard processes and assets to projects. | Ensure sufficient support is available for deployment. | List of where improved or revised processes or assets are deployed | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
256 | 29 | Process Management | PCM | Improving | L3 – Defined | PCM 3.6 — Evaluate and report the effectiveness of deployed improvements | Measure and communicate the results of process improvements. | Analyze current improvement results against business and process improvement objectives. | Process improvement evaluation report | Medium | Medium | All Organisations (ML3+) | Medium–Large | Not Started
257 | 29 | Process Management | PCM | Improving | L4 – Quantitatively Managed | PCM 4.1 — Use statistical and quantitative techniques to validate selected performance improvements | Statistically validate that performance improvements meet expectations. | Plan the validation. | Validation plans | Medium | Low | All Organisations (ML3+) | Medium–Large | Not Started
258 | 30 | Governance | GOV | Managing | L1 – Initial / Foundation | GOV 1.1 — Senior management identifies what is important and defines the approach | Senior management sets direction and communicates objectives. | Senior management decides what is important, sets the approach, and communicates to the organization. | Identification of important items and approach to improvement | High | High | All Organisations | All | Not Started
259 | 30 | Governance | GOV | Managing | L2 – Managed / Core | GOV 2.1 — Senior management defines, keeps updated, and communicates organizational directives | Senior management establishes and communicates organizational directives. | Senior management defines and communicates organizational directives. | Organizational improvement directives | High | High | All Organisations | All | Not Started
260 | 30 | Governance | GOV | Managing | L2 – Managed / Core | GOV 2.2 — Senior management provides funding, resources, and training | Senior management ensures adequate resources for process development and improvement. | Senior management approves and provides needed funding and resources. | Recorded allocation of needed funding, training, and resources approved by senior management | High | High | All Organisations | All | Not Started
261 | 30 | Governance | GOV | Managing | L2 – Managed / Core | GOV 2.3 — Senior management identifies their information needs and uses collected information | Senior management governs and oversees process implementation and improvement. | Senior management identifies and keeps up to date their information needs. | Senior management information needs | High | High | All Organisations | All | Not Started
262 | 30 | Governance | GOV | Managing | L2 – Managed / Core | GOV 2.4 — Senior management assigns authority and holds people accountable | Senior management enforces accountability for process adherence and improvement. | Senior management reviews issues and trends related to deploying and improving processes. | Action items related to accountability | High | High | All Organisations | All | Not Started
263 | 30 | Governance | GOV | Managing | L3 – Defined | GOV 3.1 — Senior management ensures that measures are collected, analyzed, and used | Senior management verifies organizational measurement practices. | Senior management verifies measures are collected, analysed, and used. | Updated organizational measurement repository | High | Medium | All Organisations | All | Not Started
264 | 30 | Governance | GOV | Managing | L3 – Defined | GOV 3.2 — Senior management ensures competencies and processes are aligned with organizational objectives | Senior management reviews alignment of competencies and processes with objectives. | Review the status of competencies, objectives, and processes. | Results of strategy and process reviews and discussions | High | Medium | All Organisations | All | Not Started
265 | 30 | Governance | GOV | Managing | L4 – Quantitatively Managed | GOV 4.1 — Senior management verifies that selected decisions are driven by statistical and quantitative analysis | Senior management uses quantitative analysis to govern strategic decisions. | Review and discuss strategy, process performance, decisions, and progress. | Results of strategy, process performance, and progress reviews and decision analyses | High | Low | All Organisations | All | Not Started
266 | 31 | Implementation Infrastructure | II | Enabling – Organisation | L1 – Initial / Foundation | II 1.1 — Perform processes that address the intent of the Level 1 practices | Execute processes that satisfy the intent of Level 1 practices. | Perform processes. | Outputs of processes | Medium | High | All Organisations | All | Not Started
267 | 31 | Implementation Infrastructure | II | Enabling – Organisation | L2 – Managed / Core | II 2.1 — Provide sufficient resources, funding, and training | Ensure adequate resources, funding, and training for process development. | Identify and provide needed resources. | Budget for resources | Medium | High | All Organisations | All | Not Started
268 | 31 | Implementation Infrastructure | II | Enabling – Organisation | L2 – Managed / Core | II 2.2 — Develop and keep processes updated, and verify they are being followed | Document, follow, and verify adherence to processes. | Identify process purpose. | Recorded processes | Medium | High | All Organisations | All | Not Started
269 | 31 | Implementation Infrastructure | II | Enabling – Organisation | L3 – Defined | II 3.1 — Use organizational processes and process assets to plan, manage, and perform the work | Leverage organizational assets in all project work. | Plan work using organizational process assets. | Tailored process assets | Medium | Medium | All Organisations | All | Not Started
270 | 31 | Implementation Infrastructure | II | Enabling – Organisation | L3 – Defined | II 3.2 — Evaluate the adherence to and effectiveness of organizational processes | Assess whether processes are being followed and are effective. | Evaluate processes for effectiveness and usefulness. | Evaluation results | Medium | Medium | All Organisations | All | Not Started
271 | 31 | Implementation Infrastructure | II | Enabling – Organisation | L3 – Defined | II 3.3 — Contribute process-related information or process assets to the organization | Share best practices, lessons learned, and process assets with the organization. | Collect and record best practices, lessons learned, and information from tailoring. | Examples, best practices, and lessons learned | Medium | Medium | All Organisations | All | Not Started
272 | 31 | Implementation Infrastructure | II | Enabling – Organisation | L4 – Quantitatively Managed | II 4.1 — Develop the organizational capability to apply statistical and quantitative techniques | Build organizational infrastructure for statistical and quantitative analysis. | Define infrastructure required to support the use of statistical techniques. | Requirements of organizational capability for using statistical and quantitative techniques | Medium | Low | All Organisations | All | Not Started

## 📊 PA Summary & Scores
CMMI v3.0 — Practice Area Summary & Maturity Assessment
Use the Assessment Score (0–5) to record the current capability level for each Practice Area. Filter by PA Priority or Category to focus improvement efforts.
# | Practice Area | Abbrev | PA Category | Max Level | Practices Count | PA Priority | Applicability | Org Size | Target Maturity Level | Assessment Score (0–5) | Status / Notes
1 | Service Delivery Management | SDM | Doing – Service | 3 | 8 | High | IT Services / Managed Services | All
2 | Strategic Service Management | STSM | Doing – Service | 3 | 5 | Medium | IT Services / Managed Services | Medium–Large
3 | Product Integration | PI | Doing – Engineering | 3 | 10 | High | Software / Hardware / Systems Dev | All
4 | Technical Solution | TS | Doing – Engineering | 3 | 10 | High | Software / Hardware / Systems Dev | All
5 | Peer Reviews | PR | Doing – Quality | 3 | 6 | Medium | All Organisations | All
6 | Process Quality Assurance | PQA | Supporting | 3 | 6 | High | All Organisations | All
7 | Requirements Development & Management | RDM | Doing – Engineering | 3 | 13 | High | Software / IT Services / Systems Dev | All
8 | Verification & Validation | VV | Doing – Engineering | 3 | 7 | High | Software / Hardware / Systems Dev | All
9 | Supplier Agreement Management | SAM | Managing | 2 | 8 | Medium | All Organisations | All
10 | Continuity | CONT | Doing – Service | 3 | 7 | Medium | IT Services / Critical Systems | All
11 | Incident Resolution & Prevention | IRP | Doing – Service | 3 | 6 | Medium | IT Services / Operations | All
12 | Risk & Opportunity Management | RSK | Managing | 3 | 8 | High | All Organisations | All
13 | Enabling Virtual Work | EVW | Enabling – People | 3 | 6 | Low | All Organisations | All
14 | Organizational Training | OT | Enabling – People | 3 | 9 | Medium | All Organisations | All
15 | Workforce Empowerment | WE | Enabling – People | 3 | 7 | Low | All Organisations | Medium–Large
16 | Estimating | EST | Managing | 3 | 6 | High | All Organisations | All
17 | Monitor & Control | MC | Managing | 3 | 10 | High | All Organisations | All
18 | Planning | PLAN | Managing | 4 | 15 | High | All Organisations | All
19 | Data Management | DM | Enabling – Data | 3 | 6 | Medium | All Organisations | All
20 | Data Quality | DQ | Enabling – Data | 3 | 7 | Medium | All Organisations | All
21 | Enabling Safety | ESAF | Enabling – Safety & Security | 3 | 8 | Low | Safety-Critical / Manufacturing / Regulated | All
22 | Enabling Security | ESEC | Enabling – Safety & Security | 3 | 9 | High | All Organisations | All
23 | Managing Security Threats & Vulnerabilities | MST | Enabling – Safety & Security | 4 | 10 | Medium | IT / Cybersecurity-Focused Orgs | Medium–Large
24 | Causal Analysis & Resolution | CAR | Improving | 5 | 11 | Medium | All Organisations | All
25 | Configuration Management | CM | Supporting | 2 | 7 | High | Software / Systems Dev / IT Operations | All
26 | Decision Analysis & Resolution | DAR | Supporting | 3 | 8 | Low | All Organisations | All
27 | Managing Performance & Measurement | MPM | Improving | 5 | 22 | Medium | All Organisations (ML3+) | Medium–Large
28 | Process Asset Development | PAD | Improving | 3 | 10 | Medium | All Organisations (ML3+) | Medium–Large
29 | Process Management | PCM | Improving | 4 | 12 | Medium | All Organisations (ML3+) | Medium–Large
30 | Governance | GOV | Managing | 4 | 8 | High | All Organisations | All
31 | Implementation Infrastructure | II | Enabling – Organisation | 4 | 7 | Medium | All Organisations | All
| TOTAL |  |  |  | 272

## 🗂 PA Category Guide
CMMI v3.0 — Practice Area Category Reference
CMMI Practice Areas are grouped into domains. Use this reference to understand the intent of each PA and how it should be applied in a GRC context.
Practice Area | Abbrev | GRC Positioning & Context
Service Delivery Management | SDM | Core for any organization delivering IT or managed services. Less relevant for pure product-development shops.
Strategic Service Management | STSM | Important for service providers with a portfolio of services. May be lower priority for small teams or project-focused orgs.
Product Integration | PI | Critical for engineering teams that assemble complex solutions from components. Less applicable to pure service orgs.
Technical Solution | TS | Central to any development organisation. Skip or deprioritise for non-technical service delivery contexts.
Peer Reviews | PR | Broadly applicable quality practice. Prioritise for engineering-intensive programmes; adapt for documentation and process reviews in service orgs.
Process Quality Assurance | PQA | Universal applicability. Essential underpinning for any CMMI programme. Always evaluate.
Requirements Development & Management | RDM | Applies wherever stakeholder needs must be captured and managed. Fundamental to quality outcomes.
Verification & Validation | VV | Critical for regulated and safety/quality-sensitive environments. Lower priority in pure service-management contexts.
Supplier Agreement Management | SAM | Relevant wherever third-party suppliers are engaged. Prioritise for organisations with significant outsourcing or vendor dependency.
Continuity | CONT | Higher priority for service organisations with SLAs and availability obligations. Align with existing BCP/DR programmes.
Incident Resolution & Prevention | IRP | Core for IT operations and service desk teams. Less applicable in pure development contexts without operational responsibilities.
Risk & Opportunity Management | RSK | Universal. Risk management is a foundational discipline regardless of sector or size.
Enabling Virtual Work | EVW | More relevant for distributed or fully remote teams. Can be deprioritised if the organisation is co-located.
Organizational Training | OT | Broadly applicable. Prioritise in organisations with identified skill gaps or high staff turnover.
Workforce Empowerment | WE | Strategic HR-aligned practice. Lower operational priority; more relevant in culture-transformation or scaled agile contexts.
Estimating | EST | Core project management discipline. Universal applicability across project-based and product organisations.
Monitor & Control | MC | Universal project management foundation. Among the most critical PAs for programme governance.
Planning | PLAN | Universal. Planning is foundational to all CMMI practice areas and business operations.
Data Management | DM | Growing in importance with data governance regulations (GDPR, etc.). Prioritise for data-intensive or regulated organisations.
Data Quality | DQ | Critical for analytics, AI/ML, or reporting-heavy functions. Lower priority for organisations without significant data dependencies.
Enabling Safety | ESAF | Primarily relevant for safety-critical domains (aerospace, medical devices, industrial). Deprioritise for typical IT or services environments.
Enabling Security | ESEC | Universal. Security is a baseline requirement. Note: CMMI's ESEC addresses security programme maturity, not specific controls (for controls, reference ISO 27001 / NIST CSF).
Managing Security Threats & Vulnerabilities | MST | Important for organisations with significant threat exposure. Complements—but does not replace—specialist security frameworks such as NIST CSF, CIS Controls, or ISO 27001.
Causal Analysis & Resolution | CAR | Core continuous improvement discipline. Universal, but depth of analysis should scale with organisational maturity.
Configuration Management | CM | Essential for any team producing versioned work products. Higher priority in software and systems development contexts.
Decision Analysis & Resolution | DAR | Valuable but often deprioritised in early maturity stages. More relevant for organisations making complex architectural or investment decisions.
Managing Performance & Measurement | MPM | Central to CMMI's quantitative management levels. Important for organisations targeting ML3+ or establishing performance baselines.
Process Asset Development | PAD | Critical for organisations building an organisational process library. Higher priority for those targeting Level 3 and above.
Process Management | PCM | Enables governance of the process improvement programme itself. Pair with PAD and MPM for Level 3 targets.
Governance | GOV | Foundational for any GRC programme. Governance sets the tone and accountability structure for all other CMMI practice areas.
Implementation Infrastructure | II | Provides the organisational infrastructure needed to sustain CMMI practices. Higher priority at Level 3 and above.
PA Category Colour Legend
Doing – Engineering
Doing – Service
Doing – Quality
Managing
Enabling – People
Enabling – Data
Enabling – Safety & Security
Enabling – Organisation
Supporting
Improving